## Sheet1
Task | Estimated Time (Hours) | Actual Time (Hours) | Time Difference (Hours) | Total Estimated Time (Hours) | Total Logged Time (Hours)
Flow Diagram | 0.5 | 0.5 | 0 | 57.5 | 0
Weekly Work | 11.5
Tasks: | [5 empty] | Thoughts: | Summary for each task:
Physics | 12 |  |  |  |  | I want to get this working first but I forsee it taking the most time | This task should control all the physics of the game including how the ball moves and turning angles
Disruptor | 6 |  |  |  |  | This shouldn’t be too bad since I can resuse som intrrupt and flag code | This task should control the enrgy stored up so it should connect to the LED task and button press implementation
LEDs | 5 |  |  |  |  | I have already done something similar in previous labs but this is slightly more complicated | This task will control LEDs to Indicate how much energy the user has when the button is pressed
LCD | 4.5 |  |  |  |  | This might be difficult since I didn’t get lab 7 working so I have no practice with it | This task will display all functionality on the screen of the STM
Map Generation | 8 |  |  |  |  | I can work with some friends to get this running | This task should generate all Cells, Walls, Holes, and Waypoints for the labrynth
Gyro | 8 |  |  |  |  | Done a lot of this maybe I can implement message queue? | This task should collect tilt data from the gyro and should connect to the physics task to determine ball motion
Debugging | 14 |  |  |  |  | Most of my time will be spent here | This isnt a task but debugging in general