## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Physics engine doesn't work | 8 | 100 | 800 | 2024-03-20 | Accepted | A | I implement it incorrectly multiple times and spend hourts trying to fix it
Other classes get in the way and I fall behind | 8 | 70 | 320 | 2024-03-20 | Mitigated | M | If other labs take too much time I might not be able to work as much on this one
Randomly generating walls doesn't work out | 40 | 20 | 800 | 2024-03-20 | Accepted | A | If I implement this incorrectly. I can switch to hard coded walls if all else fails
First implementation of distruptor doesn’t work as expected | 100 | 40 | 4000 | 2024-03-20 | Accepted | A | Most likely will happen but I can get help so risk is not that high
My Gyro values result in LCD drift of the balls position | 70 | 20 | 1400 | 2024-04-05 | Accepted | A | If the gyro values cause drift when I am debugging it might increase time to identify an issue (eg. I am testing the ball rolling off the LCDs left hand side)
ITC doesn't work as expected(eg. I use semaphores instead of Mutex) | 8 | 40 | 320 | 2024-04-05 | Accepted | A | If I implement the wrong ITC method I could have some problems with task/data management
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100