## Sheet1
Task | Estimated Time (Hours) | Actual Time (Hours) | Time Difference (Hours) |  | Total Estimated Time (Hours) | Total Logged Time (Hours)
Flow Diagram | 0.5 | 0.5 | 0 |  | 57.5 | 22.5
Weekly Work | 11.5 | 11 | 0.5
Tasks/Work Items table: |  |  | Completion: | Task/Component Completion Statements and Judgements: |  |  | Thoughts: | Summary for each task:
Physics | 12 | 12 | Complete | I have made significant progress on this task the only thing I am missing is collisions which I will do at the same time as the maze task so I will mark it as complete. I learned how to get the angle the board is pointing from the gyro averaged raw data. |  |  | I want to get this working first but I forsee it taking the most time | This task should control all the physics of the game including how the ball moves and turning angles
Disruptor | 6 |  | Not Started | I havent started this yet. |  |  | This shouldn’t be too bad since I can resuse som intrrupt and flag code | This task should control the enrgy stored up so it should connect to the LED task and button press implementation
LEDs | 5 |  | Not Started | This goes hand in hand with the disruptor. |  |  | I have already done something similar in previous labs but this is slightly more complicated | This task will control LEDs to Indicate how much energy the user has when the button is pressed
LCD | 4.5 | 4 | Almost complete | I have my LCD task working now and it is displaying the ball rolling around so I will mark as almost complete. |  |  | This might be difficult since I didn’t get lab 7 working so I have no practice with it | This task will display all functionality on the screen of the STM
Map Generation | 8 |  | Not Started | This will be started next week. |  |  | I can work with some friends to get this running | This task should generate all Cells, Walls, Holes, and Waypoints for the labrynth
Gyro | 8 | 4 | Complete | My gyro is now properly acqiring the proper x and y data and feeding it to my physics task. I learned how to average the gyro Raw data that was used to calculate the boards angle of rotation in the Physics task |  |  | Done a lot of this maybe I can implement message queue? | This task should collect tilt data from the gyro and should connect to the physics task to determine ball motion
Debugging | 14 | 2.5 | Ongoing | Debugging is on-going for all tasks and will take the most time in my estimation |  |  | Most of my time will be spent here | This isnt a task but debugging in general