## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Physics engine doesn't work | 8 | 100 | 800 | 2024-03-20 | Owned | O | I implement it incorrectly multiple times and spend hourts trying to fix it
Other classes get in the way and I fall behind | 8 | 70 | 320 | 2024-03-20 | Owned | O | If other labs take too much time I might not be able to work as much on this one
Randomly generating walls doesn't work out | 40 | 20 | 800 | 2024-03-20 | Owned | O | If I implement this incorrectly. I can switch to hard coded walls if all else fails
First implementation of distruptor doesn’t work as expected | 100 | 40 | 4000 | 2024-03-20 | Owned | O | Most likely will happen but I can get help so risk is not that high
My Gyro values result in LCD drift of the balls position | 70 | 20 | 1400 | 2024-04-05 | Owned | O | If the gyro values cause drift when I am debugging it might increase time to identify an issue (eg. I am testing the ball rolling off the LCDs left hand side)
ITC doesn't work as expected(eg. I use semaphores instead of Mutex) | 8 | 40 | 320 | 2024-04-05 | Owned | O | If I implement the wrong ITC method I could have some problems with task/data management
ISR takes too long to fire and misses button press | 5 | 20 | 100 | 2024-04-12 | Owned | O | Since I am using the HAL provided ISR there is a chance that it doesn’t work as anticipated. This risk comes from the fact that the HAL ISR needed some tinkering in previous labs
Maze collision logic is flawed (eg. If I make ceetian boxes close to a wall a collision) | 70 | 70 | 4900 | 2024-04-12 | Owned | O | I am thinking about making certain coordinates that are 1 box away from a wall count as a collision. This logic may not work and the impact is huge on the game playability

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100